## Sheet1
ፕሮግራም | የምርምር ሙከራ ቁጥር | የምርምር ሥራ /Name of activity/ | Crop/product | Researcher(s) | ኮሞዲቲ/ Commodity | ኮምፖነንት /Component/ | የምርምር ሥራው ያለበት ደረጃ /status of an activity/ /Ongoing/ New/Re-initiated)/ | የማከናወኛ ዕቅድ ጊዜ /በበጀት ዓመት ይቀመጥ/ Duration (starting and ending budget year) EC |  | ተግባሪ ማዕከላት /Implementing Centers/ እያንዳንዱ ማዕከል ለየብቻ መገለጽ አለበት፡፡ በነጠላ ሰረዝ ተያይዞ መቀመጥ የለበትም | ለበጀት ዓመቱ የተፈቀደ በጀት/2013 | የምርምር ስራው ተጠባቂ ውጤቶች /Expected deliverables/
Food processing technology | 33-01-01 | Mango bar development using different techniques | Mango | Fikru, Milkessa, Segedu, and Fruit researcher | Food | Food product development | New | 2012-07-01 | 2015-06-30 | Melkassa | 45344.39 | Optimal extrusion processing variables on chewiness and extensibility will be identified
Food processing technology | 33-01-02 | Evaluation of nutritional properties and shelf life wheat bread enriched with black cumin | Wheat+Black cumin | Melaku T, Dr. Workneh A., Abraham G., Neima D., Cherinet K., & Tamirat K. |  |  | New | 2012-07-01 | 2014-06-30 | Kulumsa | 64937.68 | Nutritious wheat bread with optimum black cumin level will be developed
Food processing technology | 33-01-03 | Physicochemical and sensory properties of bread, cookies and biscuits formulated from wheat flour and dried stevia leave powder blends | Bread, Cookies, Biscuits | Abdela B. & Beriso M |  |  | New | 2012-07-01 | 2015-06-30 | Wondogenet | 47344 | Sweet bakery baked product with optimum stevia leaf level will be formulated for society those having interest on sweet bread without table sugar
Food processing technology | 33-01-04 | Formulation of Herbal Tea from Dried Roselle (Hibiscus sabdariffa L.) and Lemon verbena (Aloysia triphylla L.) | Hibiscus + Aloysia | Abdela B. & Beriso M |  |  | New | 2012-07-01 | 2014-12-30 | Wondogenet | 43344.69 | Herbal tea will be formulated from the dried roselle and lemon verbena which have best sensory and nutraceutical value
Food processing technology | 33-01-05 | Development of Chickpea Milk Beverage from Selected Released Varieties | Chickpea | Muhaba S &Tamirat K, Dr. Workineh, Lamsgen, Semhal M, and Deribe M |  |  | New | 2012-07-01 | 2014-06-30 | Debrezeit | 45344.37 | Chickpea products will be diversified (lactose free chickpea milk and humus)
Food processing technology | 33-01-06 | Formulation of nutritionally enhanced snack from maize, dried fish and tomato powder using extrusion | Maize+fish+tomato | Hayelom B. Beliyu, Bezayehu & Seferu |  |  | New | 2012-07-01 | 2014-06-30 | Sebeta | 45344.37 | The optimum values of nutritionally improved snack with acceptable organoleptic qualities would be known
Food processing technology | 33-01-07 | Evaluation of sorghum proportion with wheat for biscuit making quality | Sorghum | Mulate Z. Segedu , Demirew A.and Banchu A. |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Melkassa | 45344.37 | Sorghum based biscuit will be developed
Food processing technology | 33-01-08 | Evaluation of nutritional and sensory quality of baked products made from Anchote and Wheat composite flours | Wheat | Ruth B, Bilatu and Dinka M |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HQ | 212314.37 | Anchote based bread making leve and processing effect will be identified
Food processing technology | 33-01-09 | Product Development of Whey Based Thin Bulla Porridge | Bulla | Nesru Z, Biadg K, Bethel Y, Mebrat H,& Getenesh T. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Holeta | 45344.37 | Whey based porridge will be developed
Food processing technology | 33-01-10 | Development of Fish powder Blending With Different Commonly Used Spices for Sigo (Thin Paste sauce) preparation | Fish | Hayelom B. Seferu T. & Beliyu K |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Sebeta | 43344.69 | Nutritious thin paste sigo preparation from fish powder and commonly used spices would be developed
Food processing technology | 33-01-11 | Utilizations of Nile Tilapia (Oreochromis niloticus) and Cat Fish (Clarias gariepinus) for Fish Sauce Production | Fish | Hayelom B. , Seferu T. & Beliyu K |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Sebeta | 47344.36 | Fish sauce making from Nile Tilapia and Cat Fish type will be formulated
Food processing technology | 33-01-12 | Enhancement of nutritional value of foods from enset using small dried fish | Enset+Fish | Seferu T., Bizuayehu G., Hayelom B.,& Beliyu K |  | Traditional food improvement | New | 2012-07-01 | 2014-06-30 | Sebeta | 50246.47 | Information on acceptable level of dry fish powder inclusion into Kocho and bulla porridge will be known
Food processing technology | 33-01-13 | Hot sauce/paste product development | Sauce | Alemayehu, Fikru, Milkessa, Mulat, Segedu, & Shimelis A |  |  | New | 2012-07-01 | 2014-06-30 | Melkassa | 50246.47 | Optimal hot sauce processing variables on sensory evaluation will be identified
Food processing technology | 33-01-14 | Optimization of fermentation condition, mechanical kneading and particle size on injera quality | Injera | Tamirat K, Muhaba S, Workineh A, Semhal M and Derbi M |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Debrezeit | 150246.47 | Optimum injera making process will be identified
Food processing technology | 33-01-15 | The effect of particle size and milling type on sorghum flour injera making quality | Injera | Mulate Z., Milkessa, Segedu, Demirew and Banchu |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Melkassa | 50246.47 | Optimal sorghum milling type and size for injera making process will be identified
Food processing technology | 33-01-16 | Optimization of traditional fish drying process | Fish | Hayelom, Bezayehu, Seferu and Beliyu |  | Food Processing Technology | New | 2012-07-01 | 2015-06-30 | Sebeta | 50792.78 | Traditional preservation techniques of dried fish fillet and quanta would be optimized for commercialized purpose.
Food processing technology | 33-01-17 | The Study of fried Product of Potato shelf Life and Nutrient composition | Potato | Biadge K, Bethel Y, Yadesa A, Zerihun A.,& Lema T |  |  | New | 2012-07-01 | 2015-06-30 | Holeta | 256391.78 | The fried products nutritional value by different oil types and at different time interval for better shelf life will be evaluated.
Food processing technology | 33-01-18 | Effect of drying methods on physico-chemical properties of red pepper | Pepper | Milkessa, Fikru, Mulate & Demirew |  |  | New | 2012-07-01 | 2015-06-30 | Melkassa | 48608.69 | Conducive drying method on basis of color and pungency will be identified
Food processing technology | 33-01-19 | Effect of processing conditions and drying technologies in selected Horticultural crop | Horticulture | Segedu B., Ruth B., Mulate Z.,Demerew A. Abyi & Banchu |  |  | New | 2012-07-01 | 2015-06-30 | Melkassa | 52976.87 | Influence of processing condition on quality of dried fruit will be determined and An appropriate dryer will be identified
Food processing technology | 33-01-20 | Study the effect of the existing injera baking mitads on injera quality attributes and on injera keeping quality over storage and suggest improvements | Injera | Dr.Workineh A Tamirat K, Muhaba S, Lamsgen Y, Shashitu A, Deribe M &Semhal M |  |  | New | 2012-07-01 | 2015-06-30 | Debrezeit | 48608.69 | Optimized injera baking processes for the existing improved mitads for better injera nutritional, sensorial attributes and keeping quality
Food processing technology | 33-01-21 | Study the effect of different injera drying technologies on dirkosh quality and optimize the process for energy saving and better dirkosh quality | Injera | Dr.Workineh, Tamirat K, Muhaba S, Lamsgen Shashitu A, Deribe M &Semhal |  |  | New | 2012-07-01 | 2015-06-30 | Debrezeit | 52976.87 | Efficient method/s for making dirkosh with better nutritional and sensorial quality
Food processing technology | 33-01-22 | Determination & Optimization of Acrylamide Level in Roasted Coffee | Coffee | Hailu R. Girmay T. Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 50792.78 | Optimized roasting temperature of coffee beans which will give minimal amount of acrylamide level will be seat
Food processing technology | 33-01-23 | Effect of packaging materials and processing method on shelf life quality of roasted and grounded Arabica coffee (Coffea arabica L.) | Coffee | Tamene H, and Misgna B |  |  | New | 2012-07-01 | 2015-06-30 | Jimma | 50792.78 | Best packaging material with optimum shelf life period which maintain freshness of roasted and grounded coffee will be identified
Food processing technology | 33-01-24 | Effect of processing methods on nutrient content and sensory acceptance of anchote varieties | Anchote | Dinka M, Desta M. and Hailu R. |  |  | Ongoing | 2010-07-01 | 2013-06-30 | HQ | 48608.7 | Influence of processing condition on quality of anchote varieties will be determined.
Food processing technology | 33-01-25 | Effect of canning on the arcelin retention, proximate composition and bioactive compounds of bean bruchid resistant lines | Bruchid | Demirew A, Fikru, Milkessa, Alemayehu., and Birhanu A |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Melkassa | 48608.7 | Influence of canning on bean variety line arcelin retention and bioactive compound level will evaluated
Food processing technology | 33-01-26 | Effect of processing conditions on anti-nutritional factors in pulses | Pulses | Demirew A., Milkessa, Fikru, and Tigist S. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Melkassa | 52976.86 | Efficient processing condition for anti-nutritional factors of pulses will be identified
Food processing technology | 33-01-27 | Evaluation of different processing methods to improve sensory attributes of quinoa | Quinoa | Bilatu, Ruth & Mulate Z. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | HQ | 106358.86 | Efficient processing methods for making quinoa with better sensorial quality
Food quality and nutrition | 33-02-01 | Physico-chemical characterization and evaluation of pepper varieties grown at different conditions and agro-ecologies | Pepper | Milkessa , Fikru, Demirew, Mulate, Shimelis A | Food | Profiling of physicochemical and food product making quality of agricultural product | New | 2012-07-01 | 2015-06-30 | MARC | 43056.69 | Best varieties with great oleoresin and/or capsaicin will be identified
Food quality and nutrition | 33-02-02 | Evaluation of released and selected maize varieties for malting purpose | Maize | Mulate Z., Fikru, Birhanu.& Alemeshet |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 39056.69 | The released and selected maize varieties for malting quality will be evaluated and identified
Food quality and nutrition | 33-02-03 | Study on physico-chemical characterization and product developments of released and promising garlic varieties | Garlic | Deribe, Dr. Workineh, Tamirat K Lamesgen, Semhal and Gezachew |  |  | New | 2012-07-01 | 2015-06-30 | DZARC | 41056.69 | Nutritional and physical properties of released and promising varieties of garlic will be determined
Food quality and nutrition | 33-02-04 | Evaluation of yam varieties grown in southwest Ethiopia for nutritional, flour and product making quality | Yam | Misgana B, Adunya B.,& Tewodros M |  |  | New | 2012-07-01 | 2014-06-30 | JARC | 41056.69 | The nutritional value and flour making capacity of yam varieties grown in Ethiopia known
Food quality and nutrition | 33-02-05 | Geographical differentiation of tef (Eragrostis tef) | Tef | Dinka M. Samuel M.& Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87056.69 | the geographical location of teff, particularly from major producing area, will be established
Food quality and nutrition | 33-02-06 | Geographical differentiation of butter | Butter | Bilatu A.& Desalegn. D. Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 81056.69 | the origin of butter, particularly from major producing areas will be established.
Food quality and nutrition | 33-02-07 | Environmental factors on fatty acids profile and phenolic compound of linseed varieties | Linseed | Yibrah A Samuel M and Dinka M |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87933.69 | Providing information about the impact of environment on the fatty acid profile and phenolic compounds of linseed genotypes
Food quality and nutrition | 33-02-08 | The effect of growing location on amino acid, fatty acid and mineral composition of soybean | Soybean | Samuel M, Dinka M & Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 143056.69 | effect of growing environment on the fatty acid, amino acid and mineral composition of soybean genotypes will evaluated
Food quality and nutrition | 33-02-09 | Evaluation of linoleic and oleic acid contents in the oils of niger varieties and genotypes | Niger | Samuel M, Mistru T &Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 139056.69 | baseline information on oleic and linoleic acid compositions of Niger genotypes and varieties that will help breeders for selection will be determined
Food quality and nutrition | 33-02-10 | Evaluation of ripening process and chemical compositions of local banana varieties cultivated at Tekeze basin | Banana | Girmay. T Yibrah. A & Girum H. |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 41056.69 | The best techniques for banana fruit ripening would verified Nutritional composition, shelf life and sensorial quality of banana fruit would be evaluated
Food quality and nutrition | 33-02-11 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit | Avocado | Mulate Z., Demirew A, & Milkessa |  |  | Ongoing | 2011-07-01 | 2013-06-30 | MARC | 122888.69 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit
Food quality and nutrition | 33-02-12 | Characterization of major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus | Rumex | Abedela B & Beriso |  |  | Ongoing | 2011-07-01 | 2013-06-30 | WGARC | 41056.69 | major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus will be characterized
Food quality and nutrition | 33-02-13 | Screening of arabica coffee germplasm for low caffeine and high chlorogenic acid coffee genotypes | Coffee | Tamene A.,Dessie B & Dr Kassaye T |  |  | Ongoing | 2010-07-01 | 2013-06-30 | JARC | 41056.69 | low caffeine and high chlorogenic acid coffee genotypes will be identified
Food quality and nutrition | 33-02-14 | Quality parameters analysis of promising korerima cultivars of south western Ethiopia | Korerima | Belay G & Sileshi A. |  |  | Ongoing | 2010-07-01 | 2013-06-30 | Tepi | 41056.69 | Quality parameters of promising long pepper (timiz)and korerima cultivars will be determined
Food quality and nutrition | 33-02-15 | Nutritional characterization of released and promising Anchote varieties | Anchote | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HQ | 284896.69 | Nutritional of released and promising Anchote varieties will be characterized
Food quality and nutrition | 33-02-16 | Physico-chemical characterization of sheko cattle breed raw milk | Milk | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 61056.69 | Physico-chemical of sheko cattle breed raw milk will be characterized
Food quality and nutrition | 33-02-17 | Physico-chemical characterization of traditional cheese of sheko cattle breed | Cheese | Belay G., Alelegn H. Rediet W., Ararisa B., & Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 56056.69 | Physico-chemical of traditional cheese of sheko cattle breed will be characterized
Food quality and nutrition | 33-02-18 | Physico-chemical characterization of traditional butter of sheko cattle breed | Butter | Dinka M, Desta M. Dr. Kassaye and Hailu |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 41056.69 | Physico-chemical of traditional butter of sheko cattle breed will be characterized
Food quality and nutrition | 33-02-19 | Nutritional Composition and Product Making Quality Evaluation of Newly Adopted Tomato (Lycopersiconesculentum Mill.) Varieties | Tomato | Demirew, Fikru., Milkessa F., Alemayehu & Tesfa |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 41056.69 | The physicochemical quality of prossing tomato will be determined
Food quality and nutrition | 33-02-20 | Study on grain physico-chemical characteristics and pasta making quality of recently released durum wheat varieties | Wheat | Tamirat K,Dr. Workineh A, Muhaba S, Derbi M,& Semhal |  |  | Ongoing | 2011-07-01 | 2014-06-30 | DZARC | 41056.69 | The physichochemical and pasta making quality will be identifed
Food quality and nutrition | 33-02-21 | Developing calibration model method for prediction of bread wheat quality traits using NIR spectroscopy | Wheat | Cherinet , Yadessa, Neima, Melaku, Abraham Mulate, Dr. Kassaye and wheat teams | Food | Model development and validation of new analytical techniques for agricultural products | New | 2012-07-01 | 2014-06-30 | KARC | 43159.52 | The model will be used for laboratory routine analysis for bread wheat traits characterization
Food quality and nutrition | 33-02-22 | Evaluation of quality of sesame using near infrared spectroscopy | Sesame | Girmay T., Samuel M.&, Dinka M. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | HQ | 543159.52 | the quality of sesame using near infrared spectroscopy evaluated
Food quality and nutrition | 33-02-23 | Near-infrared spectroscopy calibration for finger millet and common beans quality parameters | Finger millet + Common bean | Mulate.Z, Demerew A Amare S. and Birhanu A |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 43159.52 | The NIRS model of fingermillet and commonbean will be developed
Food quality and nutrition | 33-02-24 | Formulation of composite flour using barely, orange fleshed sweet potato and dried fish powder for children within the age of 6-24 months | Barley+Spotato+Fish | Belyu K., Hayelom. B,. Bezuayehu G.& Seferu, T | Food | Nutritional enhanced food products for target groups | New | 2012-07-01 | 2014-06-30 | SARC | 40005.27 | Nutritionally enhanced composite flour would be produced
Food quality and nutrition | 33-02-25 | Nutritional assessment and enhanced food formulation for lactating women from locally available crops in west shewa Oromia region |  | Bethel Y, Biyadg K, Yadessa A., erihun A, Nesru Z,& ( economics team) |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 100005.27 | Lactating women nutritional problem will be identified Locally availabe food will be formulated for those lactating women
Food quality and nutrition | 33-02-26 | Development of barley-based snack food using twin-screw extruder | Barley | Bethel Y, Biyadg K,& Yadessa A |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 80005.27 | Enhanced extruded product formulated from Oat, Barley and Chickpea
Food quality and nutrition | 33-02-27 | Development of sorghum based instant flour for complementary food using extrusion | Sorghum | Segedu , Milkessa, Fikru., Mulate,Demirew and Banchu |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 42005.27 | Blended instant flour will be developed and quality parameter of blended flour & instant flour will be evaluated
Food quality and nutrition | 33-02-28 | Evaluation and introduction of improved nutritious recipes in school feeding program |  | Banchu, Ruth, Mulate, Milkessa, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 38005.27 | Nutrient quality of school diet will be known.
Food quality and nutrition | 33-02-29 | Development of maize based complementary foods from composite flour for children 6-23 months age | Maize | Banchu, Fikru, Alemayehu, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 40005.27 | Alternative nutritious food recipes for children will be developed
Food quality and nutrition | 33-02-30 | Development nutritionally enhanced extrude complementary food for (6-24 month) infant and young children |  | Semhal M, Tamirat K, Workineh A, Lamsgen Y, Muhaba S, Derbi M and Shashitu A |  |  | New | 2012-07-01 | 2014-06-30 | DZARC | 42005.27 | Nutritionally enhanced complementary food for (6-23 month) infant and young child will be developed.
Food quality and nutrition | 33-02-31 | Development of nutritionally enhanced porridge from tef, barley and chickpea composite flour for postnatal mothers | Porridge | Semhal M, Tamirat K, Muhaba S and Derbi M |  |  | Ongoing | 2011-07-01 | 2013-06-30 | DZARC | 38005.27 | nutrational enhanced products will be developed
Food quality and nutrition | 33-02-32 | Demonstration of recipes of sweet lupine to farmers in west, north shewa and south west shewa | Lupin | Biadeg K, Bethel Y, Cherenet A,& Belaye E. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HARC | 40005.27 | recipes of sweet lupine to farmers in west, north shewa and south west shewa will be demonstrated
Food quality and nutrition | 33-02-33 | Improvement of enset food product with proteinaceous edible mushroom | Enset+Mushroom | Abedela & Ruth |  |  | Ongoing | 2011-07-01 | 2014-06-30 | WGARC | 40005.27 | enset food product will be improved
Food quality and nutrition | 33-02-34 | Selection of efficient microbes to improve bioavailability of mineral in cereal based food | Cereals | Zerihun A. Abdi K. Yadesa A Biadig K. & Microbial biotech team | Food | Nutrient retention of improved crops and staple food products in Ethiopia | New | 2012-07-01 | 2014-06-30 | HARC | 43159.52 | Efficient yeast/LAB having degrading phytate or increasing the bioavailability of micronutrients will be drawn
Food quality and nutrition | 33-02-35 | Effect of storage materials on grain quality of soybean varieties | Soybean | Yechalew S& Kassahun W |  |  | Ongoing | 2011-07-01 | 2014-06-30 | JARC | 43159.52 | the effect of storage materials on soybean grain quality will be determined
Food safety | 33-03-1 | Detection of adulteration in milk using digital image processing (DIP) | Milk | Bezuayehu Gutema, &Zerihun | Dairy | Developing new and modefied techniques to detect fraud food | New | 2012-01-11 | 30/10/2015 | SARC | 52125.25 | New, simple and cost effective milk adultration technics will be developed
Food safety | 33-03-2 | Detection of adulteration in injera using digital image processing (DIP) | Injera | Bezuayehu Gutema, & Tamirat K. | Food |  | New | 2012-01-11 | 30/10/2015 | SARC | 53625.25 | New, simple and cost effective injera adultration technics will be developed
Food safety | 33-03-3 | Developing edible oil known adulteration detection method using FT-NIR spectroscopy | Edible Oil | YadesaA., Biadge K., Zerihun A., Bethel Y., Abdi K & Berhanu M | Food |  | New | 2012-01-11 | 30/10/2015 | HARC | 116146.28 | cost effective oil adultration techniques will be developed
Food safety | 33-03-4 | Determination of adulteration in Teff (Eragrostis tef) (Flour & ‘Injera’) | Tef | Dinka M. Samuel M. Girum H | Food |  | New | 2012-01-11 | 30/10/2015 | HQ | 281143 | Accurate flour adultration techniques will be developed
Food safety | 33-03-5 | Determination of adulteration in butter | Butter | Bilatu A. Desalegn D&. Girum H | Dairy |  | New | 2012-01-11 | 30/10/2014 | HQ | 52625.25 | Accurate butter adultration techniques will be developed
Food safety | 33-03-6 | Development of NIRS model for prediction of adulteration in roasted ground coffee and honey using near infrared spectroscopy | Coffee | Dr. Kassaye T., Hailu, and Teferi (HBRC) | Coffe |  | Ongoing | 2011-01-11 | 30/10/2014 | HQ | 50625.25 | NIRS model will be developed for detection of rosted coffe
Food safety | 33-03-7 | Utilization of spices and spices essential oil for improvement of quality and shelf life of ergo and cottage cheese | Ergo+Cottage | Sileshi. A, Belay. G. & Zerhun. A., & Gezahegn M | Spice | Utilization of preservatives to improve the safety and shelf life of food | New | 2012-01-11 | 30/11/2015 | TARC | 52625.25 | effective ergo and cottage cheese preservative spice will be adintified
Food safety | 33-03-8 | Fish preservative effect of chitosan produced from fish waste | Fish | Belyu .K, Seferu T, Bezayehu G , Hayelom B. & Fikadu H/M | Fish |  | New | 2012-01-11 | 30/11/2015 | SARC | 52825.25 | Cheese preservative effect of chitosan will beidentified
Food safety | 33-03-9 | Effect of clove powder, garlic and ginger paste on microbial quality and shelf life of chicken meat | Chicken meat | Shashitu A, Lamsgen Tamirat K, Dr. Workineh Semhal M, Deribe M, Alemayehu and HQ team | Spice |  | New | 2012-01-11 | 30/11/2015 | DARC | 51625.25 | safety and shilflife of checkin meat improving spice will be identified
Food safety | 33-03-10 | Preservative effects of Basil (Ocimum basilicum L.) and Rosemary (Rosmarinus officinalis L.) essential oils on raw meat, meat blend and fish fillet | Basil + rosemary | Abdela B. and Beriso M | Spice |  | New | 2012-01-11 | 30/11/2015 | WARC | 49625.25 | Raw meat and fish millet preservation effect of spicess will be identified
Food safety | 33-03-11 | Improvement of injera shelf life using spice’s essential oil | Injera | Girmay T.,and DARC team | Food |  | Ongoing | 2011-01-11 | 30/10/2014 | HQ | 277421.55 | Enjere shilflife improvement of essentioal oil will be identified
Food safety | 33-03-12 | Evaluating the effect of smoking and cleaning of milk equipment with different herbs and plants on safety, organoleptic and shelf life of milk and milk products | Milk | Zerihun A, Getenesh T, Bilatu A, Biadig K.,& Nesru Z. | Dairy |  | Ongoing | 2011-01-11 | 30/10/2013 | HARC | 435600.75 | Milk and milk product shelflife and safety improving smoking plant and cleaning herb will be identifed
Food safety | 33-03-13 | Determination of multi-class veterinary drug residues in animal tissue (cattle ) & its potential health risks | ?? | Ayetenew A. Yibraha A. Researchers/analysts from VDFHACA& Girum H. | Dairy | Assesment and prevention mechanisms of toxic heavy metals, mycotoxin and residue in food across food value chain | New | 2012-01-11 | 30/10/2015 | HQ | 455182.1 | does of multidrug residue and their health risk in milk and egg will be quantified
Food safety | 33-03-14 | The effect of traditional post-harvest processing and handling methods on quality attributes and aflatoxin accumulation in turmeric | Turmeric | Belay G., Sileshi A.,and Biruk H., Merga J.& ,Dinka M | Spice |  | New | 2012-01-11 | 30/10/2015 | TARC | 50225.25 | Effect off post harves prossesing and handling on aflatoxin accumulation will be quantified
Food safety | 33-03-15 | Determination of the extent of Aflatoxin M1 (AM1), OTA and Zearalenone in raw milk | Milk | Zerihun A, Mulat Z.,& Girum H. | Dairy |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&HARC | 51025.25 | Aflatoxin,Ota and Zearalenone in raw milk will be quantified
Food safety | 33-03-16 | Determination of the extent of Aflatoxin B1 and B2 (AB1 and AB2), OTA and Zearalenone in feeds of lactating cows | Feeds | Lamesgen, Y Mulat Z & Dr Girum H., | Feed |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&DARC | 50625.25 | Aflatoxin,Ota and Zearalenone in feed of lactating cow will be quantified
Food safety | 33-03-17 | Determination of the level of Aflatoxin (AB1, AG1, AB2 and AG2), Ochratoxin A, Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in Maize | Maize | Alemayehu G., Fikru, Mulat Z., Dr Girum Habte, and | Cereal |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&MARC | 48625.25 | Level of Aflatoxin, Ochratoxin A, Zearalenone, Deoxynivalenol and Fumonisins in Maize will be identified
Food safety | 33-03-18 | Determination of the extent of Ochratoxin A (OTA) in green coffee beans. | Coffee | Legesse H, Mulat Z.,& Dr Girum Habte | Coffe |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&JARC | 50025.25 | Extent of Ochratoxin A (OTA) in green coffee beans will be quantified
Food safety | 33-03-19 | Determination of the level of Aflatoxin (AB1, AG1, AB2 and AG2), Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in peanuts/groundnut | Groundnut | Mulate Z., Dr Girum H and Solomon | Pulse |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ | 49225.25 | Level of Aflatoxin (AB1, AG1, AB2 and AG2), Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in peanuts/groundnut will be quantified
Food safety | 33-03-20 | Comparative studies on the detoxification of Aflatoxin levels in maize by different chemical methods and its nutritional effects | Maize | Alemayehu G Fikru, Mulate Z., and Lealem T | Cereal |  | Ongoing | 2010-01-11 | 30/10/2013 | MARC | 49625.25 | Level of detoxification of Aflatoxin in maize using chemical method will be quantified
Food safety | 33-03-21 | Evaluation of heavy metals uptakes of lettuce (Lactuca Sativa L.) under irrigation water of Akaki River | Lettuce | Dagne B, Lamessegn &Mohammmed | Horticulture |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 259142.95 | Heavy metals uptakes of lettuce will be identified
Food safety | 33-03-22 | Characterization and identification of probiotics isolated from metata Ayib | Metata | Ayetenew A. Shashitu A & Girum Habtie | Dairy | Utilization of beneficial microbes to improve safety and shelflife of food | New | 2012-01-11 | 30/10/2015 | HQ | 49725.25 | Probiotics in metata ayib will be cheracterized and identified
Food safety | 33-03-23 | Production of Vitamin K2 using probiotic strains isolated from metata Ayib. | Metata | Ayetenew A, Yibrah A & Dr. Girum Habtie | Dairy |  | New | 2012-01-11 | 30/10/2015 | HQ | 262143 | Vitamin K will be produced using probiotics
Food safety | 33-03-24 | Evaluation of the functional properties of metata ayib and probiotic bacteria isolated from it | Metata | Ayetenew Abita, Shashitu, A and Dr. Girum Habtie | Dairy |  | New | 2012-01-11 | 30/10/2015 | HQ | 260143 | Functional properties of metata ayib will be cheracterized
Food safety | 33-03-25 | Characterization of probioticsisolated from Ethiopian traditional foods: Ergo, Injera and Siljo | Probiotics | Zerihun.A & Shashitu, A | Dairy |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 259142.95 | Probiotics in ethiopian traditional food will be cheracterized
Food safety | 33-03-26 | Characterization of probiotics isolated from Ethiopian traditional beverages: Tella and Cheka | Probiotics | Zerihun A.&Shashitu,A | Food |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 258642.95 | Probiotics in Ethiopian traditional beverage will be cheracterized
Food safety | 33-03-27 | Isolation, identification and collection of lactic acid bacteria from Okara and evaluation of their antimicrobial activity against pathogenic bacteria | Okra | Alemayeh G., Fikru W., Segedu B., and Teshome F. | Food | Study on prevalency of food borne pathogens and spoillage microbes | Ongoing | 2010-01-11 | 30/10/2013 | MARC | 49525.25 | Antimicrobial effect of LAB isolated from Okara will be evaluated
Food safety | 33-03-28 | Assessment of microbial safety status of selected commercial fish from Baro river and Alwaro preserver through the value chain to Gambela city | Fish | Seferu T. Bezayehu G., Beliyu K., & Hayelom B. | Fish | Study on prevalency of food borne pathogens and spoillage microbes | New | 2012-01-11 | 30/10/2015 | SARC | 50625.22 | Microbial safety of comercial fish along a value chain will be evaluated
8365027.9

## Sheet2
ፕሮግራም | project | የምርምር ሙከራ ቁጥር | የምርምር ሥራ /Name of activity/ | Crop/product | commodity | Researcher(s) | ኮሞዲቲ/ Commodity | ኮምፖነንት /Component/ | የምርምር ሥራው ያለበት ደረጃ /status of an activity/ /Ongoing/ New/Re-initiated)/ | የማከናወኛ ዕቅድ ጊዜ /በበጀት ዓመት ይቀመጥ/ Duration (starting and ending budget year) EC |  | ተግባሪ ማዕከላት /Implementing Centers/ እያንዳንዱ ማዕከል ለየብቻ መገለጽ አለበት፡፡ በነጠላ ሰረዝ ተያይዞ መቀመጥ የለበትም | ለበጀት ዓመቱ የተፈቀደ በጀት/2013 | የምርምር ስራው ተጠባቂ ውጤቶች /Expected deliverables/
Food quality and nutrition | 1 | 33-02-01 | Physico-chemical characterization and evaluation of pepper varieties grown at different conditions and agro-ecologies | Pepper | Horticulture | Milkessa , Fikru, Demirew, Mulate, Shimelis A | Food | Profiling of physicochemical and food product making quality of agricultural product | New | 2012-07-01 | 2015-06-30 | MARC | 43056.69 | Best varieties with great oleoresin and/or capsaicin will be identified
Food quality and nutrition | 1 | 33-02-02 | Evaluation of released and selected maize varieties for malting purpose | Maize | Cereals | Mulate Z., Fikru, Birhanu.& Alemeshet |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 39056.69 | The released and selected maize varieties for malting quality will be evaluated and identified
Food quality and nutrition | 1 | 33-02-03 | Study on physico-chemical characterization and product developments of released and promising garlic varieties | Garlic | Spices | Deribe, Dr. Workineh, Tamirat K Lamesgen, Semhal and Gezachew |  |  | New | 2012-07-01 | 2015-06-30 | DZARC | 41056.69 | Nutritional and physical properties of released and promising varieties of garlic will be determined
Food quality and nutrition | 1 | 33-02-04 | Evaluation of yam varieties grown in southwest Ethiopia for nutritional, flour and product making quality | Yam | Horticulture | Misgana B, Adunya B.,& Tewodros M |  |  | New | 2012-07-01 | 2014-06-30 | JARC | 41056.69 | The nutritional value and flour making capacity of yam varieties grown in Ethiopia known
Food quality and nutrition | 1 | 33-02-05 | Geographical differentiation of tef (Eragrostis tef) | Tef | Cereals | Dinka M. Samuel M.& Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87056.69 | the geographical location of teff, particularly from major producing area, will be established
Food quality and nutrition | 1 | 33-02-06 | Geographical differentiation of butter | Butter | animal products | Bilatu A.& Desalegn. D. Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 81056.69 | the origin of butter, particularly from major producing areas will be established.
Food quality and nutrition | 1 | 33-02-07 | Environmental factors on fatty acids profile and phenolic compound of linseed varieties | Linseed | oil seed | Yibrah A Samuel M and Dinka M |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87933.69 | Providing information about the impact of environment on the fatty acid profile and phenolic compounds of linseed genotypes
Food quality and nutrition | 1 | 33-02-08 | The effect of growing location on amino acid, fatty acid and mineral composition of soybean | Soybean | pulse | Samuel M, Dinka M & Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 143056.69 | effect of growing environment on the fatty acid, amino acid and mineral composition of soybean genotypes will evaluated
Food quality and nutrition | 1 | 33-02-09 | Evaluation of linoleic and oleic acid contents in the oils of niger varieties and genotypes | Niger | oil seed | Samuel M, Mistru T &Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 139056.69 | baseline information on oleic and linoleic acid compositions of Niger genotypes and varieties that will help breeders for selection will be determined
Food quality and nutrition | 1 | 33-02-10 | Evaluation of ripening process and chemical compositions of local banana varieties cultivated at Tekeze basin | Banana | Horticulture | Girmay. T Yibrah. A & Girum H. |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 41056.69 | The best techniques for banana fruit ripening would verified Nutritional composition, shelf life and sensorial quality of banana fruit would be evaluated
Food quality and nutrition | 1 | 33-02-11 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit | Avocado | Horticulture | Mulate Z., Demirew A, & Milkessa |  |  | Ongoing | 2011-07-01 | 2013-06-30 | MARC | 122888.69 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit
Food quality and nutrition | 1 | 33-02-12 | Characterization of major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus | Rumex | Spices | Abedela B & Beriso |  |  | Ongoing | 2011-07-01 | 2013-06-30 | WGARC | 41056.69 | major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus will be characterized
Food quality and nutrition | 1 | 33-02-13 | Screening of arabica coffee germplasm for low caffeine and high chlorogenic acid coffee genotypes | Coffee | coffee | Tamene A.,Dessie B & Dr Kassaye T |  |  | Ongoing | 2010-07-01 | 2013-06-30 | JARC | 41056.69 | low caffeine and high chlorogenic acid coffee genotypes will be identified
Food quality and nutrition | 1 | 33-02-14 | Quality parameters analysis of promising korerima cultivars of south western Ethiopia | Korerima | Spices | Belay G & Sileshi A. |  |  | Ongoing | 2010-07-01 | 2013-06-30 | Tepi | 41056.69 | Quality parameters of promising long pepper (timiz)and korerima cultivars will be determined
Food quality and nutrition | 1 | 33-02-15 | Nutritional characterization of released and promising Anchote varieties | Anchote | Horticulture | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HQ | 284896.69 | Nutritional of released and promising Anchote varieties will be characterized
Food quality and nutrition | 1 | 33-02-16 | Physico-chemical characterization of sheko cattle breed raw milk | Milk | animal products | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 61056.69 | Physico-chemical of sheko cattle breed raw milk will be characterized
Food quality and nutrition | 1 | 33-02-17 | Physico-chemical characterization of traditional cheese of sheko cattle breed | Cheese | animal products | Belay G., Alelegn H. Rediet W., Ararisa B., & Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 56056.69 | Physico-chemical of traditional cheese of sheko cattle breed will be characterized
Food quality and nutrition | 1 | 33-02-18 | Physico-chemical characterization of traditional butter of sheko cattle breed | Butter | animal products | Dinka M, Desta M. Dr. Kassaye and Hailu |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 41056.69 | Physico-chemical of traditional butter of sheko cattle breed will be characterized
Food quality and nutrition | 1 | 33-02-19 | Nutritional Composition and Product Making Quality Evaluation of Newly Adopted Tomato (Lycopersiconesculentum Mill.) Varieties | Tomato | Horticulture | Demirew, Fikru., Milkessa F., Alemayehu & Tesfa |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 41056.69 | The physicochemical quality of prossing tomato will be determined
Food quality and nutrition | 1 | 33-02-20 | Study on grain physico-chemical characteristics and pasta making quality of recently released durum wheat varieties | Wheat | Cereals | Tamirat K,Dr. Workineh A, Muhaba S, Derbi M,& Semhal |  |  | Ongoing | 2011-07-01 | 2014-06-30 | DZARC | 41056.69 | The physichochemical and pasta making quality will be identifed
Food quality and nutrition | 2 | 33-02-21 | Developing calibration model method for prediction of bread wheat quality traits using NIR spectroscopy | Wheat | Cereals | Cherinet , Yadessa, Neima, Melaku, Abraham Mulate, Dr. Kassaye and wheat teams | Food | Model development and validation of new analytical techniques for agricultural products | New | 2012-07-01 | 2014-06-30 | KARC | 43159.52 | The model will be used for laboratory routine analysis for bread wheat traits characterization
Food quality and nutrition | 2 | 33-02-22 | Evaluation of quality of sesame using near infrared spectroscopy | Sesame | oil seed | Girmay T., Samuel M.&, Dinka M. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | HQ | 543159.52 | the quality of sesame using near infrared spectroscopy evaluated
Food quality and nutrition | 2 | 33-02-23 | Near-infrared spectroscopy calibration for finger millet and common beans quality parameters | Finger millet + Common bean | pulse | Mulate.Z, Demerew A Amare S. and Birhanu A |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 43159.52 | The NIRS model of fingermillet and commonbean will be developed
Food quality and nutrition | 3 | 33-02-24 | Formulation of composite flour using barely, orange fleshed sweet potato and dried fish powder for children within the age of 6-24 months | Barley+Spotato+Fish | cereals | Belyu K., Hayelom. B,. Bezuayehu G.& Seferu, T | Food | Nutritional enhanced food products for target groups | New | 2012-07-01 | 2014-06-30 | SARC | 40005.27 | Nutritionally enhanced composite flour would be produced
Food quality and nutrition | 3 | 33-02-25 | Nutritional assessment and enhanced food formulation for lactating women from locally available crops in west shewa Oromia region |  | cereals | Bethel Y, Biyadg K, Yadessa A., erihun A, Nesru Z,& ( economics team) |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 100005.27 | Lactating women nutritional problem will be identified Locally availabe food will be formulated for those lactating women
Food quality and nutrition | 3 | 33-02-26 | Development of barley-based snack food using twin-screw extruder | Barley | cereals | Bethel Y, Biyadg K,& Yadessa A |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 80005.27 | Enhanced extruded product formulated from Oat, Barley and Chickpea
Food quality and nutrition | 3 | 33-02-27 | Development of sorghum based instant flour for complementary food using extrusion | Sorghum | Cereals | Segedu , Milkessa, Fikru., Mulate,Demirew and Banchu |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 42005.27 | Blended instant flour will be developed and quality parameter of blended flour & instant flour will be evaluated
Food quality and nutrition | 3 | 33-02-28 | Evaluation and introduction of improved nutritious recipes in school feeding program |  | Cereals | Banchu, Ruth, Mulate, Milkessa, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 38005.27 | Nutrient quality of school diet will be known.
Food quality and nutrition | 3 | 33-02-29 | Development of maize based complementary foods from composite flour for children 6-23 months age | Maize | Cereals | Banchu, Fikru, Alemayehu, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 40005.27 | Alternative nutritious food recipes for children will be developed
Food quality and nutrition | 3 | 33-02-30 | Development nutritionally enhanced extrude complementary food for (6-24 month) infant and young children |  | Cereals | Semhal M, Tamirat K, Workineh A, Lamsgen Y, Muhaba S, Derbi M and Shashitu A |  |  | New | 2012-07-01 | 2014-06-30 | DZARC | 42005.27 | Nutritionally enhanced complementary food for (6-23 month) infant and young child will be developed.
Food quality and nutrition | 3 | 33-02-31 | Development of nutritionally enhanced porridge from tef, barley and chickpea composite flour for postnatal mothers | Porridge | cereals | Semhal M, Tamirat K, Muhaba S and Derbi M |  |  | Ongoing | 2011-07-01 | 2013-06-30 | DZARC | 38005.27 | nutrational enhanced products will be developed
Food quality and nutrition | 3 | 33-02-32 | Demonstration of recipes of sweet lupine to farmers in west, north shewa and south west shewa | Lupin | pulse | Biadeg K, Bethel Y, Cherenet A,& Belaye E. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HARC | 40005.27 | recipes of sweet lupine to farmers in west, north shewa and south west shewa will be demonstrated
Food quality and nutrition | 3 | 33-02-33 | Improvement of enset food product with proteinaceous edible mushroom | Enset+Mushroom | Horticulture | Abedela & Ruth |  |  | Ongoing | 2011-07-01 | 2014-06-30 | WGARC | 40005.27 | enset food product will be improved
Food quality and nutrition | 4 | 33-02-34 | Selection of efficient microbes to improve bioavailability of mineral in cereal based food | Cereals | Cereals | Zerihun A. Abdi K. Yadesa A Biadig K. & Microbial biotech team | Food | Nutrient retention of improved crops and staple food products in Ethiopia | New | 2012-07-01 | 2014-06-30 | HARC | 43159.52 | Efficient yeast/LAB having degrading phytate or increasing the bioavailability of micronutrients will be drawn
Food quality and nutrition | 4 | 33-02-35 | Effect of storage materials on grain quality of soybean varieties | Soybean | pulse | Yechalew S& Kassahun W |  |  | Ongoing | 2011-07-01 | 2014-06-30 | JARC | 43159.52 | the effect of storage materials on soybean grain quality will be determined
8365027.9

## Sheet4
Project 1 | 20
project 2 | 3
project 3 | 10
project 4 | 2

## Lupin
statues
2013 | 10
2014 | 17
2015 | 8
Anchote | 1
Avocado | 1
Banana | 1
Barley | 2
Butter | 1
Cereals | 1
Cheese | 1
Coffee | 1
Enset+Mushroom | 1
Finger millet + Common bean | 1
Garlic | 1
Korerima | 1
Linseed | 1
Lupin | 1
Maize | 2
Milk | 1
Niger | 1

## Sheet3
program | research_no | name_of_activity | crop | researcher | commodity | component | status | start_time | end_time | center | budget | deliverable
Food processing technology | 33-01-01 | Mango bar development using different techniques | Mango | Fikru, Milkessa, Segedu, and Fruit researcher | Food | Food product development | New | 2012-07-01 | 2015-06-30 | Melkassa | 45344.39 | Optimal extrusion processing variables on chewiness and extensibility will be identified
Food processing technology | 33-01-02 | Evaluation of nutritional properties and shelf life wheat bread enriched with black cumin | Wheat+Black cumin | Melaku T, Dr. Workneh A., Abraham G., Neima D., Cherinet K., & Tamirat K. |  |  | New | 2012-07-01 | 2014-06-30 | Kulumsa | 64937.68 | Nutritious wheat bread with optimum black cumin level will be developed
Food processing technology | 33-01-03 | Physicochemical and sensory properties of bread, cookies and biscuits formulated from wheat flour and dried stevia leave powder blends | Bread, Cookies, Biscuits | Abdela B. & Beriso M |  |  | New | 2012-07-01 | 2015-06-30 | Wondogenet | 47344 | Sweet bakery baked product with optimum stevia leaf level will be formulated for society those having interest on sweet bread without table sugar
Food processing technology | 33-01-04 | Formulation of Herbal Tea from Dried Roselle (Hibiscus sabdariffa L.) and Lemon verbena (Aloysia triphylla L.) | Hibiscus + Aloysia | Abdela B. & Beriso M |  |  | New | 2012-07-01 | 2014-12-30 | Wondogenet | 43344.69 | Herbal tea will be formulated from the dried roselle and lemon verbena which have best sensory and nutraceutical value
Food processing technology | 33-01-05 | Development of Chickpea Milk Beverage from Selected Released Varieties | Chickpea | Muhaba S &Tamirat K, Dr. Workineh, Lamsgen, Semhal M, and Deribe M |  |  | New | 2012-07-01 | 2014-06-30 | Debrezeit | 45344.37 | Chickpea products will be diversified (lactose free chickpea milk and humus)
Food processing technology | 33-01-06 | Formulation of nutritionally enhanced snack from maize, dried fish and tomato powder using extrusion | Maize+fish+tomato | Hayelom B. Beliyu, Bezayehu & Seferu |  |  | New | 2012-07-01 | 2014-06-30 | Sebeta | 45344.37 | The optimum values of nutritionally improved snack with acceptable organoleptic qualities would be known
Food processing technology | 33-01-07 | Evaluation of sorghum proportion with wheat for biscuit making quality | Sorghum | Mulate Z. Segedu , Demirew A.and Banchu A. |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Melkassa | 45344.37 | Sorghum based biscuit will be developed
Food processing technology | 33-01-08 | Evaluation of nutritional and sensory quality of baked products made from Anchote and Wheat composite flours | Wheat | Ruth B, Bilatu and Dinka M |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HQ | 212314.37 | Anchote based bread making leve and processing effect will be identified
Food processing technology | 33-01-09 | Product Development of Whey Based Thin Bulla Porridge | Bulla | Nesru Z, Biadg K, Bethel Y, Mebrat H,& Getenesh T. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Holeta | 45344.37 | Whey based porridge will be developed
Food processing technology | 33-01-10 | Development of Fish powder Blending With Different Commonly Used Spices for Sigo (Thin Paste sauce) preparation | Fish | Hayelom B. Seferu T. & Beliyu K |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Sebeta | 43344.69 | Nutritious thin paste sigo preparation from fish powder and commonly used spices would be developed
Food processing technology | 33-01-11 | Utilizations of Nile Tilapia (Oreochromis niloticus) and Cat Fish (Clarias gariepinus) for Fish Sauce Production | Fish | Hayelom B. , Seferu T. & Beliyu K |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Sebeta | 47344.36 | Fish sauce making from Nile Tilapia and Cat Fish type will be formulated
Food processing technology | 33-01-12 | Enhancement of nutritional value of foods from enset using small dried fish | Enset+Fish | Seferu T., Bizuayehu G., Hayelom B.,& Beliyu K |  | Traditional food improvement | New | 2012-07-01 | 2014-06-30 | Sebeta | 50246.47 | Information on acceptable level of dry fish powder inclusion into Kocho and bulla porridge will be known
Food processing technology | 33-01-13 | Hot sauce/paste product development | Sauce | Alemayehu, Fikru, Milkessa, Mulat, Segedu, & Shimelis A |  |  | New | 2012-07-01 | 2014-06-30 | Melkassa | 50246.47 | Optimal hot sauce processing variables on sensory evaluation will be identified
Food processing technology | 33-01-14 | Optimization of fermentation condition, mechanical kneading and particle size on injera quality | Injera | Tamirat K, Muhaba S, Workineh A, Semhal M and Derbi M |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Debrezeit | 150246.47 | Optimum injera making process will be identified
Food processing technology | 33-01-15 | The effect of particle size and milling type on sorghum flour injera making quality | Injera | Mulate Z., Milkessa, Segedu, Demirew and Banchu |  |  | Ongoing | 2011-07-01 | 2014-12-30 | Melkassa | 50246.47 | Optimal sorghum milling type and size for injera making process will be identified
Food processing technology | 33-01-16 | Optimization of traditional fish drying process | Fish | Hayelom, Bezayehu, Seferu and Beliyu |  | Food Processing Technology | New | 2012-07-01 | 2015-06-30 | Sebeta | 50792.78 | Traditional preservation techniques of dried fish fillet and quanta would be optimized for commercialized purpose.
Food processing technology | 33-01-17 | The Study of fried Product of Potato shelf Life and Nutrient composition | Potato | Biadge K, Bethel Y, Yadesa A, Zerihun A.,& Lema T |  |  | New | 2012-07-01 | 2015-06-30 | Holeta | 256391.78 | The fried products nutritional value by different oil types and at different time interval for better shelf life will be evaluated.
Food processing technology | 33-01-18 | Effect of drying methods on physico-chemical properties of red pepper | Pepper | Milkessa, Fikru, Mulate & Demirew |  |  | New | 2012-07-01 | 2015-06-30 | Melkassa | 48608.69 | Conducive drying method on basis of color and pungency will be identified
Food processing technology | 33-01-19 | Effect of processing conditions and drying technologies in selected Horticultural crop | Horticulture | Segedu B., Ruth B., Mulate Z.,Demerew A. Abyi & Banchu |  |  | New | 2012-07-01 | 2015-06-30 | Melkassa | 52976.87 | Influence of processing condition on quality of dried fruit will be determined and An appropriate dryer will be identified
Food processing technology | 33-01-20 | Study the effect of the existing injera baking mitads on injera quality attributes and on injera keeping quality over storage and suggest improvements | Injera | Dr.Workineh A Tamirat K, Muhaba S, Lamsgen Y, Shashitu A, Deribe M &Semhal M |  |  | New | 2012-07-01 | 2015-06-30 | Debrezeit | 48608.69 | Optimized injera baking processes for the existing improved mitads for better injera nutritional, sensorial attributes and keeping quality
Food processing technology | 33-01-21 | Study the effect of different injera drying technologies on dirkosh quality and optimize the process for energy saving and better dirkosh quality | Injera | Dr.Workineh, Tamirat K, Muhaba S, Lamsgen Shashitu A, Deribe M &Semhal |  |  | New | 2012-07-01 | 2015-06-30 | Debrezeit | 52976.87 | Efficient method/s for making dirkosh with better nutritional and sensorial quality
Food processing technology | 33-01-22 | Determination & Optimization of Acrylamide Level in Roasted Coffee | Coffee | Hailu R. Girmay T. Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 50792.78 | Optimized roasting temperature of coffee beans which will give minimal amount of acrylamide level will be seat
Food processing technology | 33-01-23 | Effect of packaging materials and processing method on shelf life quality of roasted and grounded Arabica coffee (Coffea arabica L.) | Coffee | Tamene H, and Misgna B |  |  | New | 2012-07-01 | 2015-06-30 | Jimma | 50792.78 | Best packaging material with optimum shelf life period which maintain freshness of roasted and grounded coffee will be identified
Food processing technology | 33-01-24 | Effect of processing methods on nutrient content and sensory acceptance of anchote varieties | Anchote | Dinka M, Desta M. and Hailu R. |  |  | Ongoing | 2010-07-01 | 2013-06-30 | HQ | 48608.7 | Influence of processing condition on quality of anchote varieties will be determined.
Food processing technology | 33-01-25 | Effect of canning on the arcelin retention, proximate composition and bioactive compounds of bean bruchid resistant lines | Bruchid | Demirew A, Fikru, Milkessa, Alemayehu., and Birhanu A |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Melkassa | 48608.7 | Influence of canning on bean variety line arcelin retention and bioactive compound level will evaluated
Food processing technology | 33-01-26 | Effect of processing conditions on anti-nutritional factors in pulses | Pulses | Demirew A., Milkessa, Fikru, and Tigist S. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | Melkassa | 52976.86 | Efficient processing condition for anti-nutritional factors of pulses will be identified
Food processing technology | 33-01-27 | Evaluation of different processing methods to improve sensory attributes of quinoa | Quinoa | Bilatu, Ruth & Mulate Z. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | HQ | 106358.86 | Efficient processing methods for making quinoa with better sensorial quality
Food quality and nutrition | 33-02-01 | Physico-chemical characterization and evaluation of pepper varieties grown at different conditions and agro-ecologies | Pepper | Milkessa , Fikru, Demirew, Mulate, Shimelis A | Food | Profiling of physicochemical and food product making quality of agricultural product | New | 2012-07-01 | 2015-06-30 | MARC | 43056.69 | Best varieties with great oleoresin and/or capsaicin will be identified
Food quality and nutrition | 33-02-02 | Evaluation of released and selected maize varieties for malting purpose | Maize | Mulate Z., Fikru, Birhanu.& Alemeshet |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 39056.69 | The released and selected maize varieties for malting quality will be evaluated and identified
Food quality and nutrition | 33-02-03 | Study on physico-chemical characterization and product developments of released and promising garlic varieties | Garlic | Deribe, Dr. Workineh, Tamirat K Lamesgen, Semhal and Gezachew |  |  | New | 2012-07-01 | 2015-06-30 | DZARC | 41056.69 | Nutritional and physical properties of released and promising varieties of garlic will be determined
Food quality and nutrition | 33-02-04 | Evaluation of yam varieties grown in southwest Ethiopia for nutritional, flour and product making quality | Yam | Misgana B, Adunya B.,& Tewodros M |  |  | New | 2012-07-01 | 2014-06-30 | JARC | 41056.69 | The nutritional value and flour making capacity of yam varieties grown in Ethiopia known
Food quality and nutrition | 33-02-05 | Geographical differentiation of tef (Eragrostis tef) | Tef | Dinka M. Samuel M.& Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87056.69 | the geographical location of teff, particularly from major producing area, will be established
Food quality and nutrition | 33-02-06 | Geographical differentiation of butter | Butter | Bilatu A.& Desalegn. D. Girum H |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 81056.69 | the origin of butter, particularly from major producing areas will be established.
Food quality and nutrition | 33-02-07 | Environmental factors on fatty acids profile and phenolic compound of linseed varieties | Linseed | Yibrah A Samuel M and Dinka M |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 87933.69 | Providing information about the impact of environment on the fatty acid profile and phenolic compounds of linseed genotypes
Food quality and nutrition | 33-02-08 | The effect of growing location on amino acid, fatty acid and mineral composition of soybean | Soybean | Samuel M, Dinka M & Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 143056.69 | effect of growing environment on the fatty acid, amino acid and mineral composition of soybean genotypes will evaluated
Food quality and nutrition | 33-02-09 | Evaluation of linoleic and oleic acid contents in the oils of niger varieties and genotypes | Niger | Samuel M, Mistru T &Yibrah A |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 139056.69 | baseline information on oleic and linoleic acid compositions of Niger genotypes and varieties that will help breeders for selection will be determined
Food quality and nutrition | 33-02-10 | Evaluation of ripening process and chemical compositions of local banana varieties cultivated at Tekeze basin | Banana | Girmay. T Yibrah. A & Girum H. |  |  | New | 2012-07-01 | 2015-06-30 | HQ | 41056.69 | The best techniques for banana fruit ripening would verified Nutritional composition, shelf life and sensorial quality of banana fruit would be evaluated
Food quality and nutrition | 33-02-11 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit | Avocado | Mulate Z., Demirew A, & Milkessa |  |  | Ongoing | 2011-07-01 | 2013-06-30 | MARC | 122888.69 | The effect of different agro-ecology and ripening stages on oil yields and its nutritional profile of selected avocado fruit
Food quality and nutrition | 33-02-12 | Characterization of major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus | Rumex | Abedela B & Beriso |  |  | Ongoing | 2011-07-01 | 2013-06-30 | WGARC | 41056.69 | major beverage colorant and standardization of HMPs from roots of Rumexabyssinicus will be characterized
Food quality and nutrition | 33-02-13 | Screening of arabica coffee germplasm for low caffeine and high chlorogenic acid coffee genotypes | Coffee | Tamene A.,Dessie B & Dr Kassaye T |  |  | Ongoing | 2010-07-01 | 2013-06-30 | JARC | 41056.69 | low caffeine and high chlorogenic acid coffee genotypes will be identified
Food quality and nutrition | 33-02-14 | Quality parameters analysis of promising korerima cultivars of south western Ethiopia | Korerima | Belay G & Sileshi A. |  |  | Ongoing | 2010-07-01 | 2013-06-30 | Tepi | 41056.69 | Quality parameters of promising long pepper (timiz)and korerima cultivars will be determined
Food quality and nutrition | 33-02-15 | Nutritional characterization of released and promising Anchote varieties | Anchote | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HQ | 284896.69 | Nutritional of released and promising Anchote varieties will be characterized
Food quality and nutrition | 33-02-16 | Physico-chemical characterization of sheko cattle breed raw milk | Milk | Belay G., Alelegn H. Rediet W., Ararisa B.,& Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 61056.69 | Physico-chemical of sheko cattle breed raw milk will be characterized
Food quality and nutrition | 33-02-17 | Physico-chemical characterization of traditional cheese of sheko cattle breed | Cheese | Belay G., Alelegn H. Rediet W., Ararisa B., & Gezahegn M. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 56056.69 | Physico-chemical of traditional cheese of sheko cattle breed will be characterized
Food quality and nutrition | 33-02-18 | Physico-chemical characterization of traditional butter of sheko cattle breed | Butter | Dinka M, Desta M. Dr. Kassaye and Hailu |  |  | Ongoing | 2011-07-01 | 2013-06-30 | Tepi | 41056.69 | Physico-chemical of traditional butter of sheko cattle breed will be characterized
Food quality and nutrition | 33-02-19 | Nutritional Composition and Product Making Quality Evaluation of Newly Adopted Tomato (Lycopersiconesculentum Mill.) Varieties | Tomato | Demirew, Fikru., Milkessa F., Alemayehu & Tesfa |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 41056.69 | The physicochemical quality of prossing tomato will be determined
Food quality and nutrition | 33-02-20 | Study on grain physico-chemical characteristics and pasta making quality of recently released durum wheat varieties | Wheat | Tamirat K,Dr. Workineh A, Muhaba S, Derbi M,& Semhal |  |  | Ongoing | 2011-07-01 | 2014-06-30 | DZARC | 41056.69 | The physichochemical and pasta making quality will be identifed
Food quality and nutrition | 33-02-21 | Developing calibration model method for prediction of bread wheat quality traits using NIR spectroscopy | Wheat | Cherinet , Yadessa, Neima, Melaku, Abraham Mulate, Dr. Kassaye and wheat teams | Food | Model development and validation of new analytical techniques for agricultural products | New | 2012-07-01 | 2014-06-30 | KARC | 43159.52 | The model will be used for laboratory routine analysis for bread wheat traits characterization
Food quality and nutrition | 33-02-22 | Evaluation of quality of sesame using near infrared spectroscopy | Sesame | Girmay T., Samuel M.&, Dinka M. |  |  | Ongoing | 2011-07-01 | 2014-06-30 | HQ | 543159.52 | the quality of sesame using near infrared spectroscopy evaluated
Food quality and nutrition | 33-02-23 | Near-infrared spectroscopy calibration for finger millet and common beans quality parameters | Finger millet + Common bean | Mulate.Z, Demerew A Amare S. and Birhanu A |  |  | Ongoing | 2011-07-01 | 2014-06-30 | MARC | 43159.52 | The NIRS model of fingermillet and commonbean will be developed
Food quality and nutrition | 33-02-24 | Formulation of composite flour using barely, orange fleshed sweet potato and dried fish powder for children within the age of 6-24 months | Barley+Spotato+Fish | Belyu K., Hayelom. B,. Bezuayehu G.& Seferu, T | Food | Nutritional enhanced food products for target groups | New | 2012-07-01 | 2014-06-30 | SARC | 40005.27 | Nutritionally enhanced composite flour would be produced
Food quality and nutrition | 33-02-25 | Nutritional assessment and enhanced food formulation for lactating women from locally available crops in west shewa Oromia region |  | Bethel Y, Biyadg K, Yadessa A., erihun A, Nesru Z,& ( economics team) |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 100005.27 | Lactating women nutritional problem will be identified Locally availabe food will be formulated for those lactating women
Food quality and nutrition | 33-02-26 | Development of barley-based snack food using twin-screw extruder | Barley | Bethel Y, Biyadg K,& Yadessa A |  |  | New | 2012-07-01 | 2014-06-30 | HARC | 80005.27 | Enhanced extruded product formulated from Oat, Barley and Chickpea
Food quality and nutrition | 33-02-27 | Development of sorghum based instant flour for complementary food using extrusion | Sorghum | Segedu , Milkessa, Fikru., Mulate,Demirew and Banchu |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 42005.27 | Blended instant flour will be developed and quality parameter of blended flour & instant flour will be evaluated
Food quality and nutrition | 33-02-28 | Evaluation and introduction of improved nutritious recipes in school feeding program |  | Banchu, Ruth, Mulate, Milkessa, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 38005.27 | Nutrient quality of school diet will be known.
Food quality and nutrition | 33-02-29 | Development of maize based complementary foods from composite flour for children 6-23 months age | Maize | Banchu, Fikru, Alemayehu, Segadu and Demirew |  |  | New | 2012-07-01 | 2014-06-30 | MARC | 40005.27 | Alternative nutritious food recipes for children will be developed
Food quality and nutrition | 33-02-30 | Development nutritionally enhanced extrude complementary food for (6-24 month) infant and young children |  | Semhal M, Tamirat K, Workineh A, Lamsgen Y, Muhaba S, Derbi M and Shashitu A |  |  | New | 2012-07-01 | 2014-06-30 | DZARC | 42005.27 | Nutritionally enhanced complementary food for (6-23 month) infant and young child will be developed.
Food quality and nutrition | 33-02-31 | Development of nutritionally enhanced porridge from tef, barley and chickpea composite flour for postnatal mothers | Porridge | Semhal M, Tamirat K, Muhaba S and Derbi M |  |  | Ongoing | 2011-07-01 | 2013-06-30 | DZARC | 38005.27 | nutrational enhanced products will be developed
Food quality and nutrition | 33-02-32 | Demonstration of recipes of sweet lupine to farmers in west, north shewa and south west shewa | Lupin | Biadeg K, Bethel Y, Cherenet A,& Belaye E. |  |  | Ongoing | 2011-07-01 | 2013-06-30 | HARC | 40005.27 | recipes of sweet lupine to farmers in west, north shewa and south west shewa will be demonstrated
Food quality and nutrition | 33-02-33 | Improvement of enset food product with proteinaceous edible mushroom | Enset+Mushroom | Abedela & Ruth |  |  | Ongoing | 2011-07-01 | 2014-06-30 | WGARC | 40005.27 | enset food product will be improved
Food quality and nutrition | 33-02-34 | Selection of efficient microbes to improve bioavailability of mineral in cereal based food | Cereals | Zerihun A. Abdi K. Yadesa A Biadig K. & Microbial biotech team | Food | Nutrient retention of improved crops and staple food products in Ethiopia | New | 2012-07-01 | 2014-06-30 | HARC | 43159.52 | Efficient yeast/LAB having degrading phytate or increasing the bioavailability of micronutrients will be drawn
Food quality and nutrition | 33-02-35 | Effect of storage materials on grain quality of soybean varieties | Soybean | Yechalew S& Kassahun W |  |  | Ongoing | 2011-07-01 | 2014-06-30 | JARC | 43159.52 | the effect of storage materials on soybean grain quality will be determined
Food safety | 33-03-1 | Detection of adulteration in milk using digital image processing (DIP) | Milk | Bezuayehu Gutema, &Zerihun | Dairy | Developing new and modefied techniques to detect fraud food | New | 2012-01-11 | 30/10/2015 | SARC | 52125.25 | New, simple and cost effective milk adultration technics will be developed
Food safety | 33-03-2 | Detection of adulteration in injera using digital image processing (DIP) | Injera | Bezuayehu Gutema, & Tamirat K. | Food |  | New | 2012-01-11 | 30/10/2015 | SARC | 53625.25 | New, simple and cost effective injera adultration technics will be developed
Food safety | 33-03-3 | Developing edible oil known adulteration detection method using FT-NIR spectroscopy | Edible Oil | YadesaA., Biadge K., Zerihun A., Bethel Y., Abdi K & Berhanu M | Food |  | New | 2012-01-11 | 30/10/2015 | HARC | 116146.28 | cost effective oil adultration techniques will be developed
Food safety | 33-03-4 | Determination of adulteration in Teff (Eragrostis tef) (Flour & ‘Injera’) | Tef | Dinka M. Samuel M. Girum H | Food |  | New | 2012-01-11 | 30/10/2015 | HQ | 281143 | Accurate flour adultration techniques will be developed
Food safety | 33-03-5 | Determination of adulteration in butter | Butter | Bilatu A. Desalegn D&. Girum H | Dairy |  | New | 2012-01-11 | 30/10/2014 | HQ | 52625.25 | Accurate butter adultration techniques will be developed
Food safety | 33-03-6 | Development of NIRS model for prediction of adulteration in roasted ground coffee and honey using near infrared spectroscopy | Coffee | Dr. Kassaye T., Hailu, and Teferi (HBRC) | Coffe |  | Ongoing | 2011-01-11 | 30/10/2014 | HQ | 50625.25 | NIRS model will be developed for detection of rosted coffe
Food safety | 33-03-7 | Utilization of spices and spices essential oil for improvement of quality and shelf life of ergo and cottage cheese | Ergo+Cottage | Sileshi. A, Belay. G. & Zerhun. A., & Gezahegn M | Spice | Utilization of preservatives to improve the safety and shelf life of food | New | 2012-01-11 | 30/11/2015 | TARC | 52625.25 | effective ergo and cottage cheese preservative spice will be adintified
Food safety | 33-03-8 | Fish preservative effect of chitosan produced from fish waste | Fish | Belyu .K, Seferu T, Bezayehu G , Hayelom B. & Fikadu H/M | Fish |  | New | 2012-01-11 | 30/11/2015 | SARC | 52825.25 | Cheese preservative effect of chitosan will beidentified
Food safety | 33-03-9 | Effect of clove powder, garlic and ginger paste on microbial quality and shelf life of chicken meat | Chicken meat | Shashitu A, Lamsgen Tamirat K, Dr. Workineh Semhal M, Deribe M, Alemayehu and HQ team | Spice |  | New | 2012-01-11 | 30/11/2015 | DARC | 51625.25 | safety and shilflife of checkin meat improving spice will be identified
Food safety | 33-03-10 | Preservative effects of Basil (Ocimum basilicum L.) and Rosemary (Rosmarinus officinalis L.) essential oils on raw meat, meat blend and fish fillet | Basil + rosemary | Abdela B. and Beriso M | Spice |  | New | 2012-01-11 | 30/11/2015 | WARC | 49625.25 | Raw meat and fish millet preservation effect of spicess will be identified
Food safety | 33-03-11 | Improvement of injera shelf life using spice’s essential oil | Injera | Girmay T.,and DARC team | Food |  | Ongoing | 2011-01-11 | 30/10/2014 | HQ | 277421.55 | Enjere shilflife improvement of essentioal oil will be identified
Food safety | 33-03-12 | Evaluating the effect of smoking and cleaning of milk equipment with different herbs and plants on safety, organoleptic and shelf life of milk and milk products | Milk | Zerihun A, Getenesh T, Bilatu A, Biadig K.,& Nesru Z. | Dairy |  | Ongoing | 2011-01-11 | 30/10/2013 | HARC | 435600.75 | Milk and milk product shelflife and safety improving smoking plant and cleaning herb will be identifed
Food safety | 33-03-13 | Determination of multi-class veterinary drug residues in animal tissue (cattle ) & its potential health risks | ?? | Ayetenew A. Yibraha A. Researchers/analysts from VDFHACA& Girum H. | Dairy | Assesment and prevention mechanisms of toxic heavy metals, mycotoxin and residue in food across food value chain | New | 2012-01-11 | 30/10/2015 | HQ | 455182.1 | does of multidrug residue and their health risk in milk and egg will be quantified
Food safety | 33-03-14 | The effect of traditional post-harvest processing and handling methods on quality attributes and aflatoxin accumulation in turmeric | Turmeric | Belay G., Sileshi A.,and Biruk H., Merga J.& ,Dinka M | Spice |  | New | 2012-01-11 | 30/10/2015 | TARC | 50225.25 | Effect off post harves prossesing and handling on aflatoxin accumulation will be quantified
Food safety | 33-03-15 | Determination of the extent of Aflatoxin M1 (AM1), OTA and Zearalenone in raw milk | Milk | Zerihun A, Mulat Z.,& Girum H. | Dairy |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&HARC | 51025.25 | Aflatoxin,Ota and Zearalenone in raw milk will be quantified
Food safety | 33-03-16 | Determination of the extent of Aflatoxin B1 and B2 (AB1 and AB2), OTA and Zearalenone in feeds of lactating cows | Feeds | Lamesgen, Y Mulat Z & Dr Girum H., | Feed |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&DARC | 50625.25 | Aflatoxin,Ota and Zearalenone in feed of lactating cow will be quantified
Food safety | 33-03-17 | Determination of the level of Aflatoxin (AB1, AG1, AB2 and AG2), Ochratoxin A, Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in Maize | Maize | Alemayehu G., Fikru, Mulat Z., Dr Girum Habte, and | Cereal |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&MARC | 48625.25 | Level of Aflatoxin, Ochratoxin A, Zearalenone, Deoxynivalenol and Fumonisins in Maize will be identified
Food safety | 33-03-18 | Determination of the extent of Ochratoxin A (OTA) in green coffee beans. | Coffee | Legesse H, Mulat Z.,& Dr Girum Habte | Coffe |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ&JARC | 50025.25 | Extent of Ochratoxin A (OTA) in green coffee beans will be quantified
Food safety | 33-03-19 | Determination of the level of Aflatoxin (AB1, AG1, AB2 and AG2), Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in peanuts/groundnut | Groundnut | Mulate Z., Dr Girum H and Solomon | Pulse |  | Ongoing | 2009-01-11 | 30/10/2013 | HQ | 49225.25 | Level of Aflatoxin (AB1, AG1, AB2 and AG2), Zearalenone, Deoxynivalenol and Fumonisins (FB1and FB2) in peanuts/groundnut will be quantified
Food safety | 33-03-20 | Comparative studies on the detoxification of Aflatoxin levels in maize by different chemical methods and its nutritional effects | Maize | Alemayehu G Fikru, Mulate Z., and Lealem T | Cereal |  | Ongoing | 2010-01-11 | 30/10/2013 | MARC | 49625.25 | Level of detoxification of Aflatoxin in maize using chemical method will be quantified
Food safety | 33-03-21 | Evaluation of heavy metals uptakes of lettuce (Lactuca Sativa L.) under irrigation water of Akaki River | Lettuce | Dagne B, Lamessegn &Mohammmed | Horticulture |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 259142.95 | Heavy metals uptakes of lettuce will be identified
Food safety | 33-03-22 | Characterization and identification of probiotics isolated from metata Ayib | Metata | Ayetenew A. Shashitu A & Girum Habtie | Dairy | Utilization of beneficial microbes to improve safety and shelflife of food | New | 2012-01-11 | 30/10/2015 | HQ | 49725.25 | Probiotics in metata ayib will be cheracterized and identified
Food safety | 33-03-23 | Production of Vitamin K2 using probiotic strains isolated from metata Ayib. | Metata | Ayetenew A, Yibrah A & Dr. Girum Habtie | Dairy |  | New | 2012-01-11 | 30/10/2015 | HQ | 262143 | Vitamin K will be produced using probiotics
Food safety | 33-03-24 | Evaluation of the functional properties of metata ayib and probiotic bacteria isolated from it | Metata | Ayetenew Abita, Shashitu, A and Dr. Girum Habtie | Dairy |  | New | 2012-01-11 | 30/10/2015 | HQ | 260143 | Functional properties of metata ayib will be cheracterized
Food safety | 33-03-25 | Characterization of probioticsisolated from Ethiopian traditional foods: Ergo, Injera and Siljo | Probiotics | Zerihun.A & Shashitu, A | Dairy |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 259142.95 | Probiotics in ethiopian traditional food will be cheracterized
Food safety | 33-03-26 | Characterization of probiotics isolated from Ethiopian traditional beverages: Tella and Cheka | Probiotics | Zerihun A.&Shashitu,A | Food |  | Ongoing | 2010-01-11 | 30/10/2013 | HQ | 258642.95 | Probiotics in Ethiopian traditional beverage will be cheracterized
Food safety | 33-03-27 | Isolation, identification and collection of lactic acid bacteria from Okara and evaluation of their antimicrobial activity against pathogenic bacteria | Okra | Alemayeh G., Fikru W., Segedu B., and Teshome F. | Food | Study on prevalency of food borne pathogens and spoillage microbes | Ongoing | 2010-01-11 | 30/10/2013 | MARC | 49525.25 | Antimicrobial effect of LAB isolated from Okara will be evaluated
Food safety | 33-03-28 | Assessment of microbial safety status of selected commercial fish from Baro river and Alwaro preserver through the value chain to Gambela city | Fish | Seferu T. Bezayehu G., Beliyu K., & Hayelom B. | Fish | Study on prevalency of food borne pathogens and spoillage microbes | New | 2012-01-11 | 30/10/2015 | SARC | 50625.22 | Microbial safety of comercial fish along a value chain will be evaluated
8365027.9